## Sheet1
Issue | Found | Fixing | Done | Method
For the definition of classes, attribute, operation are not uniform |  |  |  | Meeting (Uniformed after discussion)
The operation process and design are not uniform (The button position is inconsistent, the frame size is inconsistent,and different ideas of function process and orders) |  |  |  | Meeting (Uniformed after discussion)
How to display the generate calendar |  |  |  | Creating a csv file in the the path of the jar executable file. Using it as a database.
How to save,generate and read the database |  |  |  | Creating a csv file. Using it as an intermediate to save the modified data.
How to store data when users add, delete a records. |  |  |  | Search online resource
How each operation page connects to other operation pages. |  |  |  | Declaring a variable on each page function to display its status. Thus, it can achieve the effect of each page interaction
How to solve when the user enters somes error messages. |  |  |  | Restricting users input on the input page(Only numbers and letters are accepted)
Reading data without comment records will report errors. |  |  |  | Calculating the length of the record and determine whether there are comments.